## Sprint Roadmap
PLAG DETECTOR ROADMAP |  |  | UML | REQUIREMENTS/PLANNING |  | ENV. SETUP | IMPLEMENTATION |  | TESTING | FEEDBACK | IMPROVEMENTS
Sprint 1 |  | Spint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6
Feb Week 1 | Feb Week 2 | Feb Week 3 | Feb Week 4 | Mar Week 1 | Mar Week 2 | Mar Week 3 | Mar Week 4 | Apr Week 1 | Apr Week 2 | Apr Week 3 | Apr Week 4
TEAM-202
MODIFICATIONS
UML CREATION
TEXT
UNIT TESTING
PRESENTATION
JAVA BACKEND
REQUIREMENT GATHERING/ PLANNING
USE CASES
INTEGRATION TESTING
PEER FEEDBACK
MODIFICATIONS
FUNCTIONALITIES
FINAL RELEASE
PROJECT RELEASE 1
ANGULAR FRONTEND
AWS HOSTING
ADDITION USE CASES